## APP1
Sub-Function | Demand Plans | Project Description | Project Owner | Estimated Budget | Y2025 Funding Budget | Project Planned Start Date | Status | Services Providor
AJYAD | AJYAD - Specialty | AJYAD - Specialty Geotech | Sameh Gomaa | 40000000 | 9374409 | 2025-10-01 | Awarded | Advance Construction Technology Services (ACTS)
AJYAD | RITZ-CARLTON | INTERIM TECHNICAL SERVICES AGREEMENT THE RITZ-CARLTON RESIDENCES | Sameh Gomaa | 328125 | 328125 | 2025-04-01 | Awarded | RITZ
AJYAD | Units Sub Division |  | Sameh Gomaa | 2000000 | 2000000 | 2026-01-01 | Awarded | Ossama Al Azzouni
AJYAD | Basement Demolition Contractor |  | Sameh Gomaa | 67115520 | 33557760 | 2026-03-26 | Awarded | SBG
AJYAD | AJYAD Marsh insurance SSJ PO |  | Maher Almadani | 500000 | 500000 | 2026-01-01 | Awarded | Marsh
Delivery | CCTV | Monitor progress & sites security | Farouq Asiri | 1832580 | 1832580 | 2025-06-01 | Awarded | AMNCO
Design Related Services | Design Peer Review Structure | Design Peer review services associated to Structure | Mohamed Elsharkawy | 5000000 | 2000000 | 2025-03-01 | Awarded | DAR ALRIYADH ENGINEERING CONSULTING WSP Middle East For Engineering Consulting Company(Ajyad) DAR ALRIYADH ENGINEERING CONSULTING (Demolishing) Saudi Diyar Consultants SAUDI CONSOLIDATED ENGINEERING CO. (KHATIB & ALAMI)
Design Related Services | Design Peer Review Traffic | Design Peer review services associated to Traffic | Nauman Faiz | 1000000 | 1000000 | 2025-03-01 | Awarded | DAR ALRIYADH ENGINEERING CONSULTING WSP Middle East For Engineering Consulting Company(Ajyad) DAR ALRIYADH ENGINEERING CONSULTING (Demolishing) Saudi Diyar Consultants SAUDI CONSOLIDATED ENGINEERING CO. (KHATIB & ALAMI)
Design Related Services | Design Peer Review Façade | Design Peer review services associated to Façade | Mohamed Elsharkawy | 1700000 | 700000 | 2025-03-01 | Awarded | DAR ALRIYADH ENGINEERING CONSULTING WSP Middle East For Engineering Consulting Company(Ajyad) DAR ALRIYADH ENGINEERING CONSULTING (Demolishing) Saudi Diyar Consultants SAUDI CONSOLIDATED ENGINEERING CO. (KHATIB & ALAMI)
Site Survey Services | Infrastructure Site Investigation for Demolition Plots A, B & C | to validate infra utilities data received from service providers. RCMC & AMANAH | Stuart Keane | 1151201 | 1151201 | 2025-12-01 | Awarded | Omraniyoun
Design Related Services | Security Building Pre-Concept Design, Structural Analysis and Demolition Strategy |  | Ashraf Samer | 4560000 | 1000000 | 2026-03-01 | Awarded | KHATIB & ALAMI
Site Survey Services | Review of Geological, Hydrogeological, Geotechnical and Environmental Studies for Impact of KSG on Flow of Zamzam Well |  | Feras Habis | 1092500 | 1092500 | 2026-03-01 | Awarded | KFUPM
KSG | RUA School Conditions Assessment |  | Niel Harris | 402187.5 | 402187.5 | 2026-03-01 | Awarded | Omraniyoun
KSG | Technical Support Agreement - Project Control Manager |  | Maher Almadani | 2640000 | 1000000 | 2026-03-01 | Awarded | Compass
KSG | Technical Support Agreement - Contracts Manager |  | Hashim AbdulQader | 1176000 | 1000000 | 2026-03-01 | Awarded | Compass
Site Survey Services | Amendment Agreement 4 to RUA-2023-028-4 Detailed Hydrogeological, Geological, and Geotechnical Study- 4 Add Plots |  | Ashraf Samer | 230000 | 230000 | 2026-03-01 | Awarded | Dar Al Handasah
AJYAD | DG | Cost Management Consultant pre Contract | Maher Almadani | 3000000 | 3000000 | 2025-12-01 | Awarded | DG Jones
AJYAD | PLP | AJYAD designer | Mohamed Elsharkawy | 99000000 | 99000000 | 2025-03-20 | Awarded | PLP Architecture International Ltd
AJYAD | PMC | Ajyad PMC | Sameh Gomaa | 15000000 | 15000000 | 2025-03-20 | Awarded | Hanmi Global Saudi Arabia
AJYAD | Saudi Diar Consultant Ajyad SC | Saudi Diar supervisor for AJYAD | Sameh Gomaa | 2000000 | 2000000 | 2025-04-01 | Awarded | Saudi Diyar Consultants
AJYAD | AJYAD Olive Arabia FM |  | Sameh Gomaa | 3000000 | 3000000 | 2025-12-01 | Awarded | Olive Arabia
Delivery | AOR | AOR - Supervision of Project Topographical Survey | Dib Ismail | 131460 | 131460 | 2025-04-01 | Awarded | Omraniyoun and Partner Consulting Engineers Company Solaiman Abdullah Elkhereiji Engineering Consultant Company (SAK)
Delivery | Security Services | The appointed security firm will be responsible for providing end-to-end security solutions for Zone A, B and C for the Demolition Areas in Main Plot, This will include designing and implementing comprehensive security strategies, managing on-site security personnel, monitoring operations, and ensuring compliance with the regulatory and safety standards outlined by the Employer. | Farouq Asiri | 500000 | 500000 | 2025-04-01 | Awarded | Amnco
Delivery | Drone, CameraTime Lapse, Live Broadcasting, and Regular Photography Services | Provide high-quality drone footage, time-lapse photography, and regular photo documentation. These services will help track the progress of the projects by ensuring accurate visual records are maintained and communicating the progress to local and international audiences via social media and online formats & Fixed Camera poles with Cameras covering a streamline of video capturing site progress. | Stuart Keane | 5000000 | 5000000 | 2025-04-01 | Awarded | Falcon
Design Related Services | CGI Production Service | Production of animated videos of the masterplan, buildings, public realm or interiors to be used as part of demonstrating the development for design approvals, Marketing and Sales requirements. | Mohamed Elsharkawy | 4000000 | 4000000 | 2025-09-01 | Awarded | CGI
Design Related Services | Design Peer Review MEP | Design Peer review services associated to MEP | Mohamed Elsharkawy | 12000000 | 12000000 | 2025-03-26 | Awarded | DAR ALRIYADH ENGINEERING CONSULTING WSP Middle East For Engineering Consulting Company(Ajyad) DAR ALRIYADH ENGINEERING CONSULTING (Demolishing) Saudi Diyar Consultants SAUDI CONSOLIDATED ENGINEERING CO. (KHATIB & ALAMI)
Design Related Services | Engineering & Government Services (AOR/EOR) | Services including designing, permitting and authority liaison services including data collection, review of submissions by LDCs for compliance with Authority requirements. | Mohammed Abduljawad | 3500000 | 3500000 | 2025-03-01 | Awarded | Omraniyoun and Partner Consulting Engineers Company Solaiman Abdullah Elkhereiji Engineering Consultant Company (SAK)
Phase 1 enablement | Contractor Alyamama | Demolition of the Existing Buildings, and Installation of Site Hoarding and Advertising Boards of RUA Main Plot -Makkah | Dib Ismail | 400000000 | 40000000 | 2025-03-01 | Awarded | ALYAMAMA
Phase 1 enablement | Enablement Works (site clearance, rock cutting, leveling to the formation level) | Phase 1 Main Plot Enabling Works | Abu Bakr Algam | 300000000 | 90000000 | 2025-06-25 | Awarded | Al Enjaz Trading And Contracting Company
Phase 1 enablement | Secondment | Technical support services JASARA & more MSA and WO | Hashim AbdulQader | 25000000 | 25000000 | 2025-03-01 | Awarded | JASARA COMPASS
Phase 1 enablement | Supervision Consultant - Dar International | Demolition of the Existing Buildings, and Installation of Site Hoarding and Advertising Boards of RUA Main Plot -Makkah | Dib Ismail | 3500000 | 3500000 | 2025-03-01 | Awarded | DAR Engineering
program CMP/DMP | Detailed Master plan (DMP) | Detailed Master Plan | Arnold Rouverand | 250377613 | 100000000 | 2026-06-01 | Awarded | AS+P International for Design Company, and Buro Happold and Partner for Engineering Consultancy Company; an unincorporated consortium
program CMP/DMP | King Salman Gate (KSG) Program Management Consultant (PgMC) | Portfolio Management Services for RUA portfolio, including Management of Design (Pre-contract stage), Construction & Handover Stage ( Post Contract Services ), to provide design management, design reviews, stakeholder management, Risk Management, Cost Management, Construction Management, Health and Safety. | Hashim AbdulQader | 458957093.3783 | 24000000 | 2025-07-01 | Awarded | AECOM
Research Services | Socioeconomic Data Collection and Impact Studies. (For Detailed BC) | Perform full survey with all household at the designated areas for data collection with statistical analyses to facilitate future plans. Assessment of the socio-economic impacts assumptions associated to Rua Al Haram development during the construction and operation phase. (Validation of the reports made by BCG as part of the Business plan Approval) | Arnold Rouverand | 3000000 | 3000000 | 2026-01-01 | Awarded | BCG, using JLL as a sub
Site Offices | Preliminaries -Site Offices - Design & Build | Renovation for the Site office in the main plot 1000 GFA | Sameh Gomaa | 37101484 | 22260890 | 2025-07-01 | Awarded | Focal Buildings Solutions
Site Offices | Site Supervision for enablement works and site offices | office for development team on site spervision | Sameh Gomaa | 10000000 | 5000000 | 2025-05-15 | Awarded | Saudi Consolidated Engineering Co. (Khatib & Alami)
Site Survey Services | Detailed Hydrological & geotechnical Studies | Site investigation & Geotechnical Work for Geological study including detailed geotechnical studies covering (Geological, Soil maps, Analysis of relevant Stakeholder data & Recommendation report) for the super-blocks and plots | Stuart Keane | 13000000 | 13000000 | 2025-06-01 | Awarded | Advance Construction Technology Services (ACTS)
Design Related Services | Temporary Shaep Amer Bus Station - Design Package |  | Rayan Alharthi | 10000000 | 5000000 | 2026-11-01 | EoI
AJYAD | AJYAD Construction Contractor | AJYAD project Construction Contractor | Sameh Gomaa | 2000000 | 500000 | 2026-01-01 | Not Start yet
AJYAD | AJYAD Construction |  | Sameh Gomaa | 4629463824 | 1000000 | 2026-09-26 | Not Start yet
Delivery | PPE | Personal Protective Equipment SAFTEY EQUIPMENT | Farouq Asiri | 75000 | 75000 | 2025-04-01 | Not Start yet
Delivery | advertising boards | Structural peer review for the design of fences and advertising boards and Demolition Works | Ahmed Abu Bakr | 400000 | 400000 | 2025-04-01 | Not Start yet
Design Related Services | Animation /Video Production Service | Providing Renderings of all external elevations and perspectives depicting the design developed by the lead design consultant. Provide Renderings of all entrance areas, lobbies, and foyers depicting the design developed by the lead design consultant. This material will be used as an extra material to be furnished for marketing and sales purposes. | Mohamed Elsharkawy | 3000000 | 3000000 | 2025-03-25 | Not Start yet
KSG | Guest Experience - Design Package | Guest Experience - Design Package | Niel Harris | 1440950 | 1440950 | 2026-07-26 | Not Start yet
KSG | Guest Experience - Construction Package | Guest Experience - Design Package | Niel Harris | 28819000 | 28819000 | 2026-12-26 | Not Start yet
Phase 1 | CMC-Phase 1A - Pre-Contract | Cost Management Consultant Phase 1A | Maher Almadani | 30000000 | 5000000 | 2026-04-26 | Not Start yet
Phase 1 | PMC-Phase 1 / PMCM | Project management and Construction Management Consultant for Phase 1 lifecycle | Niel Harris | 10000000 | 10000000 | 2025-06-01 | Not Start yet
Real Estate Services | Plot Subdivision Services | Consultation & Contracting services to develop "Survey Krouki" for RUA plots aligned with both RCMC & AMANA and to include site demarcation works | Arnold Rouverand | 3000000 | 1500000 | 2025-06-01 | Not Start yet
Real Estate Services | Sale Legal Services | Preparation of Sales Purchase Agreements (SPA), Master Community Declarations (MCD), Jointly Owned Property Declarations (JOPD) etc.… | Arnold Rouverand | 3000000 | 3000000 | 2025-06-01 | Not Start yet
Real Estate Services | Units Sub- Division Services | Consultation services for preparation of "Units Sorting Reports" to be processed digitally by Ministry of Justice to issue title deeds | Arnold Rouverand | 2500000 | 1250000 | 2025-06-01 | Not Start yet
Research Services | Retail, F&B Trade area Assessment | Retail, F&B Trade area Assessment | Arnold Rouverand | 1000000 | 900000 | 2026-01-01 | Not Start yet | BCG, using JLL as a sub
Research Services | Retail, F&B Asset Strategy- Detailed BC | To validate the CMP trade area assessment and determine updates associated to market assessment and prospective upcoming developments that might have an impact associated to Retailers, F&B in RUA. Services Major highlights; *A report outlining the results of the assessment of the trade area. *Recommendations driven by data regarding the assumptions used by the business plan of the proposed site. *Insights regarding customer segments and target markets. *Analysis of competitors and strategies, for standing out in the market. | Arnold Rouverand | 2000000 | 1000000 | 2026-01-01 | Not Start yet | BCG, using JLL as a sub
Research Services | Hospitality Market Trends and Assessment | To validate the CMP Hospitality trends and market assessment and determine analysis of upcoming trends, in the hospitality sector covering hotels, restaurants and related services. This study aims to highlight opportunities, obstacles and significant factors that shape the market to assist businesses and investors in making informed decisions. | Arnold Rouverand | 700000 | 630000 | 2025-05-01 | Not Start yet
Research Services | Hospitality Asset Strategy Detailed BC | To review the design deliverable, provide continuous feedback, and analyze upcoming trends, To evaluate a specific location to determine its suitability. This involves analyzing the local demographics, existing Hospitality market, accessibility, economic conditions, and potential for growth. Additionally, the project will include assessments for financial feasibility, architectural and design considerations, optimal hospitality level , and key performance indicators for successful development. The final report will offer data-driven insights on the viability of the site, target demographic segments, and strategies for market entry. potential operators and investors. | Arnold Rouverand | 1000000 | 500000 | 2025-05-01 | Not Start yet
Research Services | Utility Services Business Case | to revolutionize the management and delivery of essential utility services including district cooling, Sewage Treatment Plants (STP), and solid waste management, etc. to:- Enhancement of Efficiency, Environmental Sustainability, Quality Service Delivery: Life Cycle costing to support the decision of Develop versus PPP or outsource assessment. Public-Private Partnership (PPP) Model, Benchmarking, Feasibility Studies, Potential operators or investors, Assess the viability of PPP models in financing and managing utility services projects. Operation Strategies, Structure PPP agreements that align the interests of public entities and private sector partners. Establish clear frameworks for risk sharing, investment returns, and performance metrics. | Arnold Rouverand | 1000000 | 500000 | 2026-01-01 | Not Start yet | BCG, using JLL as a sub
Site Survey Services | Environmental Impact Assessment - Surveys and Studies | Environmental & ecological surveys and studies as required to obtain the NCEC (National Center for Environmental Compliance) and AMANA of the Holy Makkah or any other authorities as may be deemed required. | Abu Bakr Algam | 1000000 | 1000000 | 2025-04-01 | Not Start yet
Site Survey Services | Traffic Surveys | Site survey for traffic data collection with analysis studies & Recommendation report | Nauman Faiz | 1000000 | 1000000 | 2025-06-01 | Not Start yet
Specialty | Retail Design Guidelines (RDD) | Creation of the Retail design and delivery guidelines for all RUA portfolios including guidelines for the guidelines for the sub developer share, , Peer review | Shada Abubotain | 5000000 | 2500000 | 2025-09-01 | Not Start yet
Specialty | Smart City | Overall, Setting of RUA portfolio strategies for Smart City requirements including setting RUA's Objectives, Standards, best practices, cost-benefit Analysis, best practices, Implementation phasing, , Peer review | Anuar Noor | 3000000 | 3000000 | 2025-06-01 | Not Start yet
Specialty | Security strategies | Overall, Setting of RUA portfolio strategies for security requirements including setting RUA's Objectives, Standards, best practices, cost benefit Analysis, concerned authorities’ requirements mapping, Risk Assessment and Mitigation advisory, Peer review, etc.… | Abdulwahab Albishri | 2000000 | 1000000 | 2025-06-01 | Not Start yet
Specialty | Natural Disaster and Crisis Management | Overall, Setting of RUA portfolio strategies for handling Natural Disasters and crisis including setting RUA's Objectives, Standards, best practices, cost benefit Analysis, concerned authorities’ requirements mapping, Risk Assessment and Mitigation advisory, etc.… | Farouq Asiri | 700000 | 350000 | 2025-09-01 | Not Start yet
Specialty | FLS Consultant | Fire & Life Saftey | Farouq Asiri | 7000000 | 500000 | 2025-06-25 | Not Start yet
Specialty | Design Standardization | Creation of Design Guidelines for all building development works that are planned to start as per the phasing plan. Creation of Standards for all disciplines of the building design across the portfolio including. Enforcing RUA Identity as part of the guidelines. | Mohamed Elsharkawy | 20000000 | 10000000 | 2025-07-26 | Not Start yet
Specialty | Guest Experience: Supervision Pakage | Overall, Setting of RUA portfolio Guest journey and experience including touch points analysis, development of manual for guest journey and experience including operational requirements, , Peer review | Niel Harris | 864570 | 2000000 | 2026-12-26 | Not Start yet
Specialty | Masterplan Delivery Strategy | Review and development of The Consultant delivery strategy, setting the stage of the subsequent phases including but not limited to the DMP, the early enabling works, the approval process (in collaboration with all relevant stakeholders) as well as the development of the individual buildings and area around them. Delineating the Public (Realm, ROW, Infrastructure, Utility Buildings, Transport hubs etc.) from the Development Assets. Sub-Developer Vs. Master developer Plot assessments.Constructability Strategies.Phasing Strategies.etc.... | Ahmed Abu Bakr | 30000000 | 15000000 | 2025-09-01 | Not Start yet
Specialty | Built Environment Sustainability | Overall, Setting of RUA portfolio strategies for sustainability including setting RUA's Objectives, Standards, cost benefit Analysis, Certifications, Implementation Methodology etc.…. | Abu Bakr Algam | 3000000 | 1950000 | 2025-06-01 | Not Start yet
Phase 1 | Lead Design Consultant (LDC) -Phase 1A | Phase-1 Lead Design Consultant | Niel Harris | 670042090 | 120000000 | 2026-09-26 | RFP
AJYAD | AJYAD Post Contract CMC | Cost Management Consultant Post Contract | Maher Almadani | 20815000 | 4664563 | 2025-10-01 | Tender
Site Survey Services | SSJ-K&A-Topographical Site Survey verification project |  | Sherif Elbialy | 525000 | 525000 | 2026-11-01 | Tender | K&A
Development Operation | Technology Requirements / Services GIS Implementation | Design and implementation of systems architecture/infrastructure including the hardware, software, security requirements and network communication capacity to support Enterprise GIS implementation. Deliverables will include infrastructure resources to support the Enterprise system. The consultant to provide full implementation of best practices for utilizing cloud services and for hosting the ArcGIS solution on Rua Al Madinah premises or other hosting service provider entities inside Saudi Arabia. | Omer Thiab | 4000000 | 4000000 | 2025-06-01 | Transfered to land management ​